## Sheet1
TABLE 1: BGE CONASTONE TO GRACETON CONDUCTOR REPLACEMENT PROJECT (ITN 57792) PERMIT MATRIX (03-5-2020)
Applicable Authorizations & Permits | Required by | Regulatory Citation | Applicable Regulatory Activity & Comments | Anticipated Authorization or Permit Application Submittal Date | Anticipated/ Target or Approval Date | Comments
CPCN Mandatory Waiver w/Good Cause | Maryland Public Service Commission (PSC) | Section 7-207(b )(3 )(ii) of the PUA | Conductor replacement on existing double circuit structures. New replacements Str 2336R and 2314R i.e. existing tower to be replaced w/double circuit monopole. Above-ground conductor vangs to be replaced on 2323 Circuit only. BGE Legal to make final determination on the validity/strategy for a Mandatory Waiver Request in consideration of other recent CPCN Waiver determinations. | Submitted 12/6/2019 | 2020-03-04 | BGE Legal' s strategy for Mandatory Waiver request was to file one letter for all three PJM 5E projects. These submittal and approval dates need to verified by Dave Outen & Legal team.
Joint Nontidal Wetland Permit - MDSPGP-5/seek letter of auth. under existing BGE General Permit MDE-ACOE Auth. 18-NT-0367/201861968. | MDE Wetland and Waterways Program & Army Corps of Engineers Regulatory Branch | COMAR 26.23 Wetland protection statute; Section 404 CWA Wetlands and Waterways MD Programmatic General Permit MDSPGP-5 Category A and BGE General Permit (<5,000 s.ft. permanent fill) | Placement of temporary mats in wetland buffer for construction access and equipment staging; presently at four (4) wetland buffer locations, and three (3) wetland and wetland buffer location. Given the project will only involve temporary mats and no permanent fill, it will likely qualify for a permit modification under the existing BGE MDE General Permit 18-NT-0367/201861968. | Not Required | N/A | Wetland & Wetland buffer impacts have been avoided with use of existing permitted crossings.
Grading Permit | Harford County - Department of Permits, Approvals and Inspections (see Below under permits not required) | See Below under permits not required. | Need Grading permit for two replacement poles only | Submitted 2/6/2020 | 2020-05-01 | May schedule a meeting with Harford County to get their concurrence
State Utility Access Permit | State Hwy Admin. District 4 (Baltimore & Harford Co.) | MD Motor Vehicle Law, Title 24 Overhead or Aerial Wire pull crossings and temporary guard structures were needed in state ROW | Overhead or Aerial Wire pull crossings of state roads, including: SR 23 (Norrisville Rd), SR 24 (Rocks Rd), and SR 624 (Graceton Rd) in Harford County; also Construction Entrance upgrades and/or access for temporary Guard structures require a Utility Access permit. | 2020-03-22 | 2020-07-15
County Road Utility Permit/Access Permit for Aerial Road Crossings and construction entrances to ROW | Harford County Dept. of Public Works-Highways | COBAR Title 4 | Overhead or Aerial Wire pull crossing over county roads, including potential aerial lift truck staging in some locations TBD; and, for Construction Access entrance upgrades to ROW, including for Guard structures. County roads include: Urey Rd, Amos Rd, Carea Rd, Telegraph Rd, Eden Mill Rd, Fawn Grove Rd, Rd, Boggs Rd. | 2019-03-29 | 2020-06-15
Other Permits Evaluated - Not Required
Railroad Utility Permit | There are no railroad crossings for this ROW |  | N/A | N/A
FAA Obstruction/Notification Review (Lighting & Markings) & Permit (if necessary) | Federal Aviation Administration (FAA); MDOT-Maryland Aviation Administration | Title 14 of the Code of Federal Regulations; 14 CFR Part 77 | Two new replacement structures are proposed, however, there are no airports within 20,000 linear feet. Specifically, the structures do not meet the following FAA applicable notification criterion: §77.9 (b) Any construction or alteration that exceeds an imaginary surface extending outward and upward at any of the following slopes: (1) 100 to 1 for a horizontal distance of 20,000 ft. from the nearest point of the nearest runway of each airport described in paragraph (d) of this section with its longest runway more than 3,200 ft. in actual length. | N/A |  | N/A
MAA Obstruction/Notification Review (Lighting & Markings) & Permit (if necessary) | MDOT-Maryland Aviation Administration | COMAR 11.03.05.05 | MAA uses the same applicable notification criterion as the FAA noted above. Notification not applicable for this project. | N/A |  | N/A
Notes: 1) Permit application submittal and approval dates based on Construction/Outage Start date of 9/15/2020