## Sheet1
TABLE 1: BGE RAPHAEL ROAD TO NORTHEAST CONDUCTOR REPLACEMENT PROJECT (ITN 58415) PERMIT MATRIX (03-5-2020)
Applicable Authorizations & Permits | Required by | Regulatory Citation | Applicable Regulatory Activity & Comments (updated) | Permit Application submitted or Target Submittal Date | Anticipated/ Target or Approval Date | Comments/Updates
CPCN Mandatory Waiver | Maryland Public Service Commission (PSC) | Section 7-207(b )(3 )(ii) of the PUA | Mandatory Waiver request to be prepared by BGE LRE and Legal w/support from POWER Eng. - Transmission & Env. Div. | 2019-11-20 | 2020-03-04 | PJM 5E Projects CPCN Waiver Hearing to be held 2/26/2020.
Joint Nontidal Wetland Permit - MDSPGP-5 | MDE Wetland and Waterways Program & Army Corps of Engineers Regulatory Branch | COMAR 26.23 Wetland protection statute; Section 404 CWA Wetlands and Waterways MD Programmatic General Permit MDSPGP-5 Category A and BGE General Permit (<5,000 s.ft. permanent fill) | Placement of temporary mats in wetland, wetland buffer & floodplain for construction access and equipment staging, and installation of guys at Str. 2021 & foundation reinforcement @ 2023; specifically, access and/or staging mats for Str. 2007, 2010, 2014, 2019, 2020 in wetland buffer, and 2012, 2015, 2021 & 2022, 2023/2024 in wetland & buffer. | Submitted 01/02/2020 | 2020-06-01 | Rec'd MDE-DNR RTE review from Lori Byrne/DNR 1/9/2020, and MHT review Beth Cole 11/22/19. MDE 45-day public notice review completed; followed up on review status w/Cheryl Kerr 2/21/20; overall no concerns rec'd from other departments; rec'd MDE request for site visit to 2023 fnd. Reinforcement in floodplain. March 11th field visit scheduled.
Grading Permit incl./approved Grading and Erosion & Sediment Control Plan | Baltimore County - Department of Permits, Approvals and Inspections; Department of Environmental Protection and Resource Management; Department of Environmental Protection and Sustainability; Planning and Zoning - Department Review Committee (DRC) | Title 1 Subtitle 04 Excavating, Grading, Sediment Control; Section 1.04 of the Code of the Baltimore County Regulations (COBAR); and, Title 3: Protection of Water Quality, Streams, Forest Protection, Stream, Wetlands and Floodplains. | Temporary access and equipment staging, including construction mats, and temporary excavation for new guys. | 2019-12-20 | 2020-06-01 | Rec'd 1st Round of reviw comments from BC Soil Conservation District (SCD); submitted 2nd Review Grading Plan set 2/03/2020. Jim Burkman trying to schedule meeting with Baltimore County to expedite approval date.
State Utility Access Permit (MD SR 43 & Sr 40 Baltimore County) | State Hwy Admin. District 4 | MD Motor Vehicle Law, Title 24 Overhead or Aerial Wire pull crossings and temporary guard structures where needed in state ROW | Overhead or Aerial Wire pull crossings at SR 43 & SR40; construction Access entrances to ROW will not be needed as ROW entry will not occur at state road crossing, and temporary guard structures at SR 43 crossing not feasible since it’s a bridge at this wire crossing (assume airlift guards at this crossing); SR 40 may have temporary guard structures on east side of SR 40, and will need Utility Permit for staging Airlift in median of SR 40. | 2020-02-27 | 2020-04-16
County Road Utility Permit/Access Permit for Aerial Road Crossings and construction entrances to ROW | Baltimore Bureau of Highways - Dept. of Public Works | COBAR Title 4 | Overhead or Aerial Wire pull crossing, including traffic mgt. County road ROW; and, Construction Access entrances where needed to ROW. County road crossings include: Ebenezer Rd., Red Lion Rd., New Forge Rd., and Allender Rd., & five other small crossings; assume County road crossing guard structures will be located in BGE ROW. | 2020-02-28 | 2020-04-24
Railroad Crossing Utility Permit | CSX Transportation Inc | All utility activity over, in or along railroad property requires notification, detailed review & authorization prior construction. BGE has an existing License Agreement (i.e. Original Agreement for wire crossing). Reconductor work will not require access in the Railroad ROW, therefore can file online Outside Party Request Form (OPRF) for notification and authorization; will require Contractor Insurance and coordination for flagmen during wire pull operations. | Overhead or Aerial Wire pull crossing between Str. 2010 & 2011. Online application submittal - CSX-OPRF Application; following Assurance Review, contact w/ freight rail scheduler and Operations for flagmen during wire pull. | 2020-02-03 | 2020-03-30 | Crossing near Rte. 40 crossing; rec'd permit authorization; next step contact Scheduler and Flagmen coordinator; and, Gary Bowers, BGE Real Estate is working on BGE Insurance Certificate.
rec'd perm
FAA Obstruction/Notification Review (Lighting & Markings) & Permit (if necessary) | Federal Aviation Administration (FAA); MDOT-Maryland Aviation Administration | Title 14 of the Code of Federal Regulations; 14 CFR Part 77 | No new structures/heights proposed. Airlift/crane for above-ground structure work assumed to below existing tower height. | N/A | N/A
MAA Obstruction/Notification Review (Lighting & Markings) & Permit (if necessary) | MDOT-Maryland Aviation Administration | COMAR 11.03.05 | No new structures/heights proposed. Airlift/crane for above-ground structure work assumed to below existing tower height. | N/A | N/A
Notes: 1) Permit application submittal and approval dates based on Construction/Outage Work Plan start date of 3/2/2020 for "maintenance work" and reconductoring 9/15-12/15/2020